## Review
Service rollout ¦ delivery review
Snapshot date | 2026-09-30
Completed milestones | 2
Overdue milestones | 2
Update the snapshot date, due dates and progress to review another scenario.
Regenerate the Word/PDF review from the revised CSV for distribution.

## Milestones
Milestone | Owner | DueDate | Progress | Status | NextAction
Discovery sign-off | Ana | 2026-09-04 | 100% | Done | Archive the approved scope
Access model | Paweł | 2026-09-18 | 100% | Done | Keep the approval evidence
Data migration rehearsal | Markus | 2026-09-25 | 75% | Overdue | Approve the retry window and migration owner
Support handover | Chloé | 2026-09-29 | 50% | Overdue | Confirm the on-call rota and escalation path
User acceptance | Saoirse | 2026-10-09 | 40% | On track | Book acceptance testing with business owners
Release approval | Aleksandra | 2026-10-16 | 0% | On track | Review acceptance results before approving release