## Slide 1
Choose the next service investment
NORTHWIND / GOVERNANCE REVIEW / SYNTHETIC ESTIMATES
1 / Keep current
No new spend Manual triage continues Review in three months
2 / Improve intake
Six-week pilot EUR 4,800 estimate Reversible first step
3 / Replace platform
Larger investment Procurement required Longer lead time
Notes: Explain the assumptions behind each estimate. The green panel identifies the proposed option, not an approved commitment.

## Slide 2
Decision requested: approve a bounded pilot
Outcome
Measure time spent assigning requests. Use the same baseline and pilot definition.
Approval record
Sponsor: to be named Budget: illustrative EUR 4,800 Review: after six weeks Stop if ownership is unresolved
Notes: Record approval, conditions and the named sponsor in the actual governance record. This deck is a fictional example.