## Report
Name
Prepare the pilot
Pilot ready
Run the pilot
Pilot accepted
Roll out the service
Service handover

## Status and groups
UID | Name | Status | Group
1 | Prepare the pilot | Task; critical
2 | Pilot ready | Task; critical
3 | Run the pilot | Task; critical
4 | Pilot accepted | Task; critical
5 | Roll out the service | Task; critical
6 | Service handover | Task; critical

## Dependencies
Predecessor UID | Successor UID | Type | Lag
1 | 2 | Finish to start (FS) | 0
2 | 3 | Finish to start (FS) | 0
3 | 4 | Finish to start (FS) | 0
4 | 5 | Finish to start (FS) | 0
5 | 6 | Finish to start (FS) | 0