# Business case: service intake

NORTHWIND / INVESTMENT REVIEW / ILLUSTRATIVE ESTIMATE

Decide whether a shared intake form is worth a six-week pilot. The baseline is 240 requests per month; every amount below is an estimate.

## Compare the options

| Option | One-off cost | Monthly saving | Trade-off |
| --- | --- | --- | --- |
| Keep current queues | EUR 0 | EUR 0 | Manual triage continues |
| Improve the existing form | EUR 4,800 | EUR 700 | Limited reporting |
| Build a shared intake | EUR 9,600 | EUR 1,200 | Needs an owning team |

## Recommendation and sensitivity

Pilot the existing-form improvement first. At the estimated saving, simple payback is about seven months; at half the saving it is about fourteen. This excludes tax, financing and ongoing support cost.

## Next actions

- Finance: replace estimates with a full cost model.

- Operations: measure triage time before and during the pilot.

- Sponsor: review results before committing to a wider rollout.